Mississippi River Regional Planning Commission Staff Report on Projects for the Bimonthly Meeting on 4.8.2026

| Agenda Topic or Project Name | Purpose, Benefit, Project Deliverables, Contract | Project Time Period | Project Status | # Contact |
| --- | --- | --- | --- | --- |
| La Crosse County HMP | Hazard Mitigation Plan | June 2025 – December 2026 | Contracted with County to complete. Project is moving along. Jack has more meetings scheduled with communities to review risks, hazards, vulnerable populations, hazard response capabilities and mitigation project lists. Second milestone achieved per contract. We may be able to apply for past BRIC previously approved and upheld in court must apply by 4/17. | Jack Zabrowski and Jon Bingol |
| Hazard Mitigation Plan Updates – Jackson and Buffalo Counties | Hazard Mitigation Plan | June 2025 – December 2027 | Gave proposal to Jackson County, new EM is most likely looking for help and we will be reapplying for past BRIC dollars that had been approved FY24-25 and cancelled. Buffalo County is going to update their plan in-house as new BRIC excludes HMP; I offered assistance if they want or need any. | Jon Bingol |
| Town of Maiden Rock Comp Plan | Town’s comp plan | 2025 - 2026 | Town of Maiden Rock Planning Commission met in March with Ken, and set goals and other sections of the plan. | Ken Harwood |
| Scenic Mississippi Regional Transit (SMRT) bus serving Crawford, Vernon, Monroe, and La Crosse counties | Develop a fixed route public transportation service for Crawford, La Crosse, Monroe, and Vernon Counties. Bus transportation will service commuters, elderly, disabled, medical appointments, and personal travel. Funding comes from a federal DOT grant, local governments, corporate donations, Bremer Foundation Grants, and the fare box. | Service Began on December 3, 2012 -present | La Crosse County met in December to decide to include it in County budget, they have contacted partners to see if $s can be contributed for 2026 as others also removed it from their budgets. Participating counties and groups do not seem favorable on making needed investment to share the cost of SMRT. The MPO is conducting a study to consider a Regional Transportation Authority which might provide alternatives but will not be done until mid-late 2026. The County leaders are keeping us posted as the project progresses. | Ken Harwood/ Jon Bingol |
| DOT Contract Work Plan | WisDOT is beginning to update the State Freight Plan. In addition, the LAPC is in the process of updating the MPO Plan, Beyond Coulee Vision 2040. | Ongoing | The 2026 Work Plan has been approved by WisDOT. Ongoing efforts are focused on executing the 2026 tasks and maintaining collaboration on MPO transitions and planning updates. WisDOT is moving up deadlines for the 2027 Plan and we will need to approve it in August. Also, the Title VI Plan needs to be updated by December. | Ken Harwood and Jon Bingol |
| Monroe County Economic Development Committee | Assisting the Committee as needed | Ongoing | Group held the 2026 MC EDT Summit for March 30 and 31 at Havenwood Event Center and it was successful with over 120 registrations and the program was well received. | Jon Bingol |
| Vernon County Economic Development Committee RLF | County EDC approved a new loan manual and MRRPC to administer the fund. Will be paid for actual costs, time and materials. | Ongoing | MRRPC to administer the RLF and ED committee is updating the VCEDLF manual. We collect payments and manage loan requests. | Jon Bingol & Sarah Ofte |
| Monroe County WEDC Thrive Rural recipient | Community Development project in Norwalk | February 2026 – December 2027 | This second cohort of WEDC Thrive Rural grants just kicked off on 2/3/26. Jon has been included on the leadership team (like the Gays Mills project). Monroe County kickoff is 2/12/26. Norwalk leadership is considering options for the project in April. | Jon Bingol |
| Village of Oakdale Outdoor Rec Plan | Complete Village’s 5 year CORP | November 2025 – April 2026 | Sent proposed contract to Village to do CORP on 10/1 per their request. In 2026 budget, was approved at 12/15 Village Board meeting. Work is being done on the Plan. | Kia Kling & Ken H |
| Northern Grain Belt Port Statistical Area | Ability to have data on volume of goods shipped through the ports | Ongoing | The team is meeting with stakeholders to look at next steps and how best to improve the organizational structure to go after more funding for local projects. Working with La Crosse Area Port Authority to determine structure options and proposed linkage to NGBP. Still moving forward…slowly. Our group met to discuss plans to move forward and establish next steps for La Crosse and PDC ports this fall both Chambers signed MOU. Efforts have restarted and LC Chamber is taking a larger role. | Ken Harwood & Jon |
| Town of Burns Comprehensive Plan | Township asked MRRPC to update their plan. | 2024 - 2026 | Jack Zabrowski attended the Town of Burns Town Board meeting on Nov. 13 to confirm initiation of the Comp Plan process creation. Jack presented final goals and objectives for Town review and the plan is nearing completion. | Jack Zabrowski |
| City of Arcadia Comprehensive Plan | City asked MRRPC to update their plan. | 2025 - 2026 | City selected us to do the Comp Plan. Group has been meeting monthly and survey is out with versions in both Spanish and English. Survey completed and group is working on goals and remaining elements. | Kia Kling |
| Pierce County EDC | Develop strong partnership and connection with EDO. | ongoing | Working to build stronger connections. We have been meeting and plan to work with WEDC to look at creating a Façade Improvement Plan for several communities. They may want help administering the fund if it is created. Several BCF prospects identified. Group contributed $2k to Pitch Contest. | Jon Bingol |
| City of Galesville | City asked MRRPC to update their plan. | 8/2025 – 9/26 | We have been selected to do their comp plan. Kickoff meeting on 8/19/25. Survey is completed and results were shared with their Plan Commission. Goals and objectives updated, plan going well. | Jack Zabrowksi |
| Town of Garden Valley Comprehensive Plan | Town asked MRRPC to update the plan. Group is working on land use information. | 2024-2026 | Ken working with them on goals for the plan. Plan was put on hold due to issues with a metallic mining operation and legal questions. Town won zoning challenge. Ken making requested updates. | Ken Harwood |
| Crawford County Housing Task Force | Developing actionable strategies to improve housing in the county | ongoing | The County reviewed recently completed Housing Study done by SWWRPC and are determining steps to utilize the data and improve plan but group has slowed down on this effort. Ken attending 4/8 and will continue offering assistance. | Jon Bingol and Ken Harwood |
| Jackson County ED committee | Advance and enhance economic development in the county | ongoing | We participate in monthly committee meetings. We conducted a community survey and will follow up with an employee survey Ken presented information to group in January. County hired an Economic Development & Tourism Director – Ken Pearson, he started on 1/26/26. Group moving forward. | Jon Bingol, Ken Harwood & Kia Kling |
| Gays Mills Thrive Project WEDC ORP | Gays Mills is developing plans to build a community pavilion and applying for planning $s thru WEDC | April 2024 - 2026 | The team reviewed updated RFPs for initial planning work and selected engineering firm. Awarded second $25,000 grant. We will help them with a community survey to assist in creating a community development plan, survey closed 98 reponses | Jon Bingol |
| LCEDLF Committee | La Crosse County originally created this Committee to build the West Salem Industrial Park and approve loans in the EDA RLF (defed) | 1990s - 2025 | La Crosse County (LCC) disbanded the LCEDLF Committee and moved funds from Associated Bank to La Crosse County. One remaining loan has updated loan document redirecting payment to LCC. County Board created an Economic Development Committee to continue their efforts. | Jon Bingol & Sarah Ofte |
| Town of Clayton | Comp Plan | 2026 | Town of Clayton to met on 10/8 to review proposal and approved using MRRPC to do the plan update. They will start in February or March 2026. Some key committee members were out of the area. | Ken Harwood |
| CRBC New Direction | CRBC Board recently adopted a new Strategic Plan to focus on more impactful businesses for incubation and acceleration | ongoing | Jon is President in 2026. Group to partner with SBDC, Score, WWBIC, Seven Rivers, La Crosse County others to host a resource center onsite to promote business development and have “office hours” at the facility. Team has created space for resource center and dedicated space for Wi Sys Venture Home program and may get grant dollars to assist with it but did not have interest in first cohort. Joined consortium to support LADCO application for WEDC Ignite grant, they did not get big grant but did get $10,000 to do some entrepreneurial training in the area. Selected new PT Director started 2/23. | Jon Bingol |
| BRF planning grant for Connector Trail | City awarded a DOT TAP grant to connect bike path and identify river crossing and early | September 2024 – December 2026 | BRF Bike Ped Study to explore the expansion of an existing 4-mile paved recreational trail to connect with other areas of the City and the County. Plan will require engineering to develop river crossing. MRRPC is a subcontractor of the City and the $80,000 grant. Contracted with Jewell for engineering. Working on next steps. | Jon Bingol, Kia Kling, Jack Zabrowski, Ken Harwood |
| Mississippi River Parkway Commission (MRPC) | Organization established to promote and advance the Great River Road, Mississippi River Trail and regional marketing & tourism | ongoing | We attend their Board meetings and provide technical assistance where and when we can. Ken also serves on the marketing committee and is assisting them with a WI Dept of Tourism JEM grant. This is an important group for our region. | Ken Harwood & Jon Bingol |
| WEDC SBD Grant | Apply for WEDC SBD grant for $250,000 for the 9-county region | October 2024 – December 2026 | We have been selected…contract approval April 9 bimonthly. Establishing parameters and informing partners of the program. Raised $44,000 match from Vernon County $10,000, La Crosse County $30,000 and Monroe County $4,000. Approved 6 loan/grants for $480,000 with $125,000 of it in grants distributed. Business Plan contest 24 submissions and top 7 selected, scheduling pitch contest for late April. | Jon Bingol |
| Audit firm CLA | Required annual government single audit | December 2026 – April 2027 | Meeting with Brock 12/22 to get plan for audit and identify data request and processes. To be presented and approved at April 8 bimonthly meeting. | Sarah Ofte & Jon Bingol |
| Town of Arcadia | Garbage Study/Project | 4/25 – 5/26 | Town received an Innovation Grant and want us to do the study. Contract to be approved April 9 bimonthly. Kia has been doing research and analyzing the data the Town shared with us. We will be establishing a local committee to look for savings…goal of project is at least 10%. Met with Town and City, identified good savings prospects working on those options. Provided a draft of findings. Finalizing plan with actual savings. | Jon Bingol & Kia Kling |
| Jackson County Comprehensive Outdoor Recreation Plan | Complete ORP for County | 1/26 – 6/30/26 | Working with County Parks Department to update their Outdoor Rec Plan. Work has begun on the Plan. | Kia Kling & Ken H |
| Clean Cities Grant | Contracted by Clean Cities to do Community Engagement and Mapping of Great River Road EV/CNG fueling sites | 2/26 – 6/27 | Told Clean Cities I wanted to present it to MRRPC Board for discussion. This is a Dept of Energy Grant dispersed through the American Lung Assoc. to Clean Cities and $30,000 contract signed setting up a kickoff meeting. | Jon Bingol |
| EDA RLF Update 5-year Plan | EDA requirement to update Cares Act RLF Plan | Due 1/30/26 | We updated the RLF Plan and have preliminary approval but need a resolution form MRRPC Board at 2/11/26 meeting to complete the process. Received approval of Plan. | Sarah Ofte and Jon Bingol |
| 3-year EDA Project Planning Grant | Apply for EDA Project Planning Grant for 4/1/26 -3/31/29 | Due 2/20/26 | We are in the process of apply for this EDA grant. We need MRRPC Board resolution/approval at 2/11/26 meeting. Submitted on 2/20 waiting for approval. | Sarah Ofte and Jon Bingol |
| MRRPC Regional Comprehensive Plan Update | 10 year Update of Plan | 11/24 - 2026 | Still gathering data to update Plan before sharing with MRRPC comp plan committee. Kia has updated data and merging it into a new document. Will work to organize the committee and survey for plan has been revised and sent to Commission for review. Plan to update progress at April meeting. | Jon Bingol & Kia Kling |
| DNR Water Quality Plan | Create a regional water quality plan | 10/1/25 – 9/30/26 | EPA approved MRRPC Regional Water Quality Study $50,000 grant and they extended deadline to March 2027 due to approval delay. Contract signed. Started on project. | Jon Bingol & Jack Zabrowski |
| Crawford County Comprehensive Plan | Update the plan | 2026 - 2027 |  | Jon and Ken |
| Oakdale CDBG Admin | DOA CDBG | 2026 – 2027? |  | Jon and Sarah |